## Sprint-5
System Name：
Pass | 5 | Pending | 0
Fail | 0 | Number of test cases: | 5
ID | Test Case Description | Test Case Procedure | Expected Output | Tested By | Test date | Result | Note
TC1 | Efficient position and styling for pictures in detail screens | Click on each restaurant on the list after inputting varied locations to view details. | Apt positioning and styling for pictures in detail screens | Irvin | 03/25/2018 | Pass
TC2 | Implement UI for showing pictures in both screens. Implement photos section in details screen | Click on each restaurant on the list after inputting varied locations to view details. | Expected appearance of pictures on the two screens along with the photo section in details. | Irvin | 03/25/2018 | Pass
TC3 | To be able to view detailed information of the restaurant clicked | Implement backend yelp API call to retrieve pictures information | Appropriate pictures of each restaurant are displayed in detail. | Irvin | 03/27/2018 | Pass
TC4 | Call detail screen when you tap on the popup of map screen | Click on each popup and it should lead to the detailed screen of the restaurant. | On clicking on map, popup appears, on further clicking on popup it shoulfd open the detail screen of the restaurant clicked. | Irvin | 03/25/2018 | Pass
TC5 | Restaurant's price category will be shown in the list of restaurants. | Open the list of restaurants and check the information about price category. | To be able to view price category for a choose restaurant in the list screen. | Sergio Brunacci | 03/25/2018 | Pass
TC6 | Restaurant's price category will be shown in the Details screen. | Open the details screen and check the information about price category. | To be able to view price category for a choose restaurant in the detail screen. | Sergio Brunacci | 03/25/2018 | Pass

## Test Report
TEST REPORT
Note:
Date
| No | Module code | Pass | Fail | Pending | Number of test cases
| 1 | Appetite | 5 | 0 | 0 | 5
|  | Sub total | 5 | 0 | 0 | 5
|  | Test coverage |  | 100 | %
|  | Test successful coverage |  | 100 | %